ISB [Aug-09] 05

Business case for: Registration, Assessment, Results and Awards Notification Business Service

Document Change History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | 06/08/09 | David Strange | First Draft for Review by TSS |
| 1.1 | 12/08/09 | Terry Knowles | Draft for internal review |
| 1.2 | 13/08/09 | Terry Knowles | Draft for internal review |
| 1.3 | 16/08/09 | Terry Knowles | Draft for comment |
| 1.4 | 01/09/09 | David Strange | Re-Issue with revisions |

1	Introduction	3

2	Business justification	3

3	“Do nothing” implications	4

4	Architecture Scope	4

4.1	Business Processes	4

4.1.1	Awards and Examination Registration	4

4.1.2	Assessment Notification, Access Arrangements & Special Considerations	5

4.1.3	Results and Awards Notifications	5

4.2	Model	5

4.3	The data framework	5

5	Stakeholder engagement	5

6	Costs and resources	5

7	Risks	5

8	Work plan and timeline	5

# Introduction

- The DCSF’s 14 – 19 Reform Program presents a new operating model for education where the focus is on the learner and not the institution. With new qualifications such as the 14-19 Diplomas learning will be delivered by a range of learning providers in a range of locations. It is critical for delivery success that these learning providers can exchange information on learners and that learners can access resources relevant to them wherever they are.

- The delivery of Diplomas commenced in September 2008 with 144 consortia of schools, colleges, learning providers offering 20,000 places on five lines of learning. By 2011 there will be 17 Diploma lines of learning available; and by 2013 there should be access to the full national entitlement meaning a place in education for every learner aged 14-19 across England.

- Although numbers involved currently are relatively small these numbers will increase rapidly. The need for interoperability between information systems to support the institutions, learning providers and learners is paramount.

- Registration, results and awards is the activity of registering a learner for a qualification and then notifying them of the results and associated award. Currently Consortia are finding difficulties co-ordinating exams registrations due to:

- The complexity of Registrations for several components making up a Line of Learning leading to a Diploma, each from a different Awarding Body and each using a different process

- The fact that Registrations must be shared amongst the Learning Providers who between them supply the learning needed for all Components of a Diploma

- To support Diplomas and other 14-19 learning arrangements, Learning Consortia, Component Awarding Bodies and Diploma Awarding Bodies will therefore need to coordinate the registration of learners, and the subsequent results and awards, where a Diploma comprises a number of component awards.

- Hence there is a need to transfer registration, results and awards information between stakeholders and between application systems.

# Business justification

There are both financial and policy drivers for business data standards in this area:

- The existence of the standard will make it possible to coordinate exam registration, assessment notification and awards across learning consortia, allowing for the possibility of automation to avoid the current manual work-arounds

- The existence of the standard will allow processes to be established that will ensure that the registrations needed by each Learner will be accomplished reliably and accurately so that Learners will be able to claim awards after learning. It is therefore very important in order to deliver the 14-19 agenda successfully

# “Do nothing” implications

If the standard is not developed and used:

- Manual work-arounds will continue to be the only way to manage the exam registration, assessment, results and awards notification for diplomas and apprenticeships. As numbers of learners and Diploma courses grow, the burdens will increase exponentially

- There will be an increase in the number of errors leading to Learners being unable to claim awards after completion of their courses.

# Architecture Scope

## Business Processes

The business processes below support the following business services:

- Awards and Examination Registration

- Reporting of Assessments, Access Arrangements & Special Considerations

- Results and Awards Notifications

### Awards and Examination Registration

| Step 5.1 Block-Reserve Award Capacity |  |  |  |
| --- | --- | --- | --- |
| Description: This process step is triggered by the date at which Learning Provider capacity is planned and reserved. In certain circumstances a Learning Provider may choose to block book a number of award places. An example of this would be where a Learning Provider buys a block of NVQ award places. The outputs from this process step are: - The Awarding Body updates its information - The Learning Provider updates its information |  |  |  |
| Roles: - This process is undertaken by the Curriculum Lead Centre. - The data is received by an Awarding Body or Bodies |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Learning Opportunity Identifier * |  | The process step covers external assessments and internal assessments under licence |  |
| Assessment Slots |  |  |  |

| Step 5.2 Identify all awards for the course |  |  |  |
| --- | --- | --- | --- |
| Description: This process step is triggered by a date – the start of term or Learning Calendar period. An individual at the curriculum lead centre identifies all the awards necessary to fulfil the requirements of each Learner’s course. The output from this process step is that all awards are identified by the Curriculum Lead Centre. |  |  |  |
| Roles: This process is undertaken by the curriculum lead centre |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Learning Opportunity Applied For: |  | 1 or more In the case of Diplomas or other unitised learning, a LO may be made up from a number of components, each of which is a LO in its own right. |  |
| Learning Provider * | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity Name * | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity Identifier * | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity Type * | Administration, identify course (record) within LP list of courses so can obtain all course details | code list |  |
| Learning Opportunity Options * | Administration, identify course (record) within LP list of courses so can obtain all course details | code list |  |
| Learning Opportunity Start Date | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity End Date | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Assessment Centre Identification * |  |  |  |
| Mode of Study * |  |  |  |
| Home Provider Identification * |  |  |  |
| Awarding Body Identification * |  | Master list required |  |
| Training Day |  | List required |  |
| Rules of Combination |  | External set of rules to define the combinations of awards needed e.g. QCDA Rules |  |

| Step 5.3 Notify/Update Learner to each Awarding Body & or DAS |  |  |  |
| --- | --- | --- | --- |
| Description: This process step is triggered by the enrolment of a student who is subsequently registered for an award. The Learning Provider notifies or updates the relevant Awarding Bodies and or the Diploma Aggregation Service with a learners registration details. The outputs from this process are: - Notification / Update data sent to the Awarding Body - Notification / Update data sent to DAS |  |  |  |
| Roles: - This process is undertaken by the Curriculum Lead Centre. - The data is received by an Awarding Body or Bodies and or DAS |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learning Opportunity Applied For |  |  |  |
| Learning Provider * | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity Name * | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity Identifier * | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity Type * | Administration, identify course (record) within LP list of courses so can obtain all course details | code list |  |
| Learning Opportunity Options * | Administration, identify course (record) within LP list of courses so can obtain all course details | code list |  |
| Learning Opportunity Start Date | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learning Opportunity End Date | Administration, identify course (record) within LP list of courses so can obtain all course details |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Assessment Estimated Result * |  |  |  |
| Learning Opportunity Options * |  |  |  |
| Assessment Centre Identification * |  |  |  |
| Registration Status * |  |  |  |

| Step 5.4 Awarding Body Confirms or Rejects Notification |  |  |  |
| --- | --- | --- | --- |
| Description: This process step is triggered by a notification or an update from a learner. The Awarding Body confirms or rejects the notification from the learning provider. Rejection is unlikely and is most commonly linked with the status of the learning provider rather than the status of the learner. The outputs from this process are: - Registered Learner - Rejected Registration |  |  |  |
| Roles: - This process is undertaken by the Awarding Body - The data is received by the Learning Provider |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learning Opportunity Identifier * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Assessment Estimated Result * |  |  |  |
| Learning Opportunity Options * |  |  |  |
| Assessment Centre Identification * |  |  |  |
| Learning Provider Identification * |  |  |  |
| Registration Status * |  |  |  |

### Assessment Notification, Access Arrangements & Special Considerations

| Step 6.1 Notify Awarding Body of Access Arrangement |  |  |  |
| --- | --- | --- | --- |
| Description: Where a Learner needs special access arrangements or facilities e.g. in relation to disability, special needs etc, this must be notified to the Awarding Body so that special arrangements can be made for assessments. The outputs from this process are: - Notified Awarding Body |  |  |  |
| Roles: - Curriculum Lead Centre - Awarding Body |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Learning Opportunity Name * |  |  |  |
| Learning Opportunity Identifier * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Award Identification * |  |  |  |
| Learning Provider Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Access Arrangement Code * |  | Code list required: e.g. for disabled or other special access needs |  |

| Step 6.2 Complete Assessments |  |  |  |
| --- | --- | --- | --- |
| Description: Assessment is carried out and result notified to Awarding Body. The Assessor may be external or in some cases the Learning Provider is authorised by the awarding Body to conduct assessments internally, in which case the Learning Provider undertakes the Assessor role. The outputs from this process are: - Assessment Results |  |  |  |
| Roles: - Learner - Assessor |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Learning Opportunity Name * |  |  |  |
| Learning Opportunity Identifier * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Assessment Actual Result * |  |  |  |
| Assessment Actual Grade * |  |  |  |

| Step 6.3 Notify Awarding Body of Special Considerations |  |  |  |
| --- | --- | --- | --- |
| Description: When the Curriculum Delivery Centre (which could be a Consortium Lead Centre) is made aware of special considerations (illness or other circumstances) and before the Awarding Body’s notification date, the Curriculum Delivery Centre may notify the circumstances to the Awarding Body, who may take these into account when determining the Result. The outputs from this process are: - Special Considerations Notification |  |  |  |
| Roles: - Curriculum Delivery Centre |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Learning Opportunity Name * |  |  |  |
| Learning Opportunity Identifier * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Award Identification * |  |  |  |
| Learning Provider Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Assessment Special Consideration Code * |  |  |  |

### Results and Awards Notifications

| Step 7.1 Make a claim for an award |  |  |  |
| --- | --- | --- | --- |
| Description: For some Diplomas (but not for all types of Award), the Curriculum Delivery Centre must make a claim for an award when it considers that all the requirements have been met. The outputs from this process are: - Award Claim |  |  |  |
| Roles: - Curriculum Delivery Centre |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Award Centre Identification * |  |  |  |
| Award Identification * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Learning Opportunity Identifier * | Component Identification | list of |  |
| Award Claim * |  |  |  |

| Step 7.2 Issue Qualification Award Results |  |  |  |
| --- | --- | --- | --- |
| Description: An Awarding Body (Diploma AB or Component AB) issues Award Results. It is triggered either by receipt of a Claim or by receipt of relevant assessments or a combination of those. In some cases an Award may be withheld whilst issues with the Award Claim are resolved. The outputs from this process are: - Withheld Claim; or - Award Results |  |  |  |
| Roles: - Awarding Body |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Award Identification * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Umbrella award result: |  |  |  |
| Assessment Actual Result * |  | For the umbrella course/diploma |  |
| Assessment Actual Grade * |  | For the umbrella course/diploma |  |
| Result Data for each comp |  | This will be a mark or a grade |  |
| Assessment Actual Result * |  | The result could be a complex set of information |  |
| Assessment Actual Grade * |  |  |  |

| Step 7.3 Resolve Claim Issues |  |  |  |
| --- | --- | --- | --- |
| Description: The Awarding Body works with the Curriculum Delivery Centre to resolve issues. The outputs from this process are: - Resolved Claim |  |  |  |
| Roles: - Awarding Body - Curriculum Delivery Centre |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Award Centre Identification * |  |  |  |
| Award Identification * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Learning Opportunity Identifier * |  |  |  |
| Award Claim * |  |  |  |
| Award Claim Withheld Reason |  |  |  |
| Award Claim Status |  |  |  |

| Step 7.4 Communicate Result to Learner |  |  |  |
| --- | --- | --- | --- |
| Description: On receipt of the results, the Curriculum Lead Centre notifies the Learner. The outputs from this process are: - Award Results |  |  |  |
| Roles: - Curriculum Lead Centre |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Award Identification * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Umbrella award result: |  |  |  |
| Assessment Actual Result * |  |  |  |
| Assessment Actual Grade * |  |  |  |
| Result Data for each comp |  |  |  |
| Assessment Actual Result * |  |  |  |
| Assessment Actual Grade * |  |  |  |

| Step 7.5 Decide on Result Enquiry |  |  |  |
| --- | --- | --- | --- |
| Description: An Examination Officer may decide to conduct an enquiry into a result The outputs from this process are: - Award Result Enquiry |  |  |  |
| Roles: - Examination Officer |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Award Identification * |  | See learning aims DB |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Award Result Query |  |  |  |

| Step 7.6 Appeal against result |  |  |  |
| --- | --- | --- | --- |
| Description: A Curriculum Lead Centre (or Learner?) may appeal against a result (before the Appeals Deadline of the Awarding Body). The outputs from this process are: - Award Results Appeal |  |  |  |
| Roles: - Curriculum Lead Centre |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Award Identification * |  | Data to come from the learning aims database |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Award Result Appeal |  |  |  |

| Step 7.7 Issue Awards |  |  |  |
| --- | --- | --- | --- |
| Description: When Awards are due, the Awarding Body will issue final results/certificates, taking into account any enquiries and appeals. The outputs from this process are: - Award Certificate |  |  |  |
| Roles: - Awarding Body |  |  |  |
| Data needed The data needed to support each of the process steps described above are summarised in the table below. Where code lists and/or agreed definitions are needed, these are indicated by ‘*’ in the comments field. |  |  |  |
| Award Identification * |  |  |  |
| Awarding Body Identification * |  |  |  |
| Learner identification: |  |  |  |
| Learner Identifier | identification |  |  |
| Given Name | Identification |  |  |
| Family Name | Identification |  |  |
| DoB | Identification |  |  |
| Addresses (domicile, current, previous) | Identification |  |  |
| Umbrella award result: |  |  |  |
| Assessment Actual Result * |  |  |  |
| Assessment Actual Grade * |  |  |  |
| Result Data for each comp |  |  |  |
| Assessment Actual Result * |  |  |  |
| Assessment Actual Grade * |  |  |  |

## Model

The proposed standard(s) will conform to the following entities and relationships of the ESCS Data Model.

.

## The data framework

| Data item | Type | Entity (BDA V2.06) | Existing code lists | Data standard | Notes |
| --- | --- | --- | --- | --- | --- |
| Addresses (domicile, current, previous) |  | Locator |  | Location |  |
| Assessment Centre Identification * | code list | Stakeholder Role/Relationship |  | Provider - hierarchy |  |
| Assessment Slots |  | Assessment, "Block Booking" |  |  |  |
| Assessment Actual Result * | code list | Assessment |  |  |  |
| Assessment Estimated Result * | code list | Assessment |  |  |  |
| Assessment Predicted Result * | code list | Assessment |  |  |  |
| Assessment Actual Grade * | code list | Assessment |  |  |  |
| Assessment Estimated Grade * | code list | Assessment |  |  |  |
| Assessment Predicted Grade * | code list | Assessment |  |  |  |
| Assessment Special Consideration Code * | code list | Assessment |  |  |  |
| Awarding Body Identification * | code list | Stakeholder Role |  |  |  |
| Award Centre Identification * | code list | Stakeholder Role |  |  |  |
| Award Identification * | code list | Qualification |  |  |  |
| Award Identification (Umbrella Award) |  | Qualification |  |  |  |
| Award Claim * | code list | Qualification |  |  |  |
| CAB Identification * | code list | Stakeholder Role/Relationship |  | Provider - hierarchy |  |
| Consortium Identifier * | code list | Stakeholder Role |  | Provider - hierarchy |  |
| Consortium Name |  | Stakeholder |  |  |  |
| Curriculum Lead Centre * | code list | Stakeholder Role/relationship |  | Provider - hierarchy |  |
| DAB Identification * | code list | Stakeholder Role/relationship |  | Provider - hierarchy |  |
| Diploma Identification * | code list | Qualification |  | Course hierarchy inc awards | includes awards |
| DoB |  | Person |  | Learner record |  |
| Family Name |  | Person |  | Learner record |  |
| Gender * | code list | Person | ISO | Learner record |  |
| Given Name |  | Person |  | Learner record |  |
| Home Provider Identification * | code list | Stakeholder Role |  | Provider - hierarchy |  |
| Learner Identifier |  | Stakeholder Role |  | Learner record |  |
| Learning Provider Identification * | code list | Stakeholder Role |  | Provider - hierarchy |  |
| Learning Opportunity Identifier * | code list | Learning Opportunity |  | Course hierarchy inc awards |  |
| Learning Opportunity Name * | code list | Learning Opportunity |  | Course hierarchy inc awards |  |
| Learning Opportunity Options * | code list | Learning Opportunity |  | Course hierarchy inc awards |  |
| Mode of Study * | code list | Learning Opportunity |  | Learning record | (Full Time, Part Time etc.) |
| Registration Status * | code list | Registration |  |  |  |
| Status of Registration * | code list | Registration |  | Exam registration |  |
| ULN |  | Stakeholder Role (Learner) |  | Learner record |  |
| Learning Opportunity Start Date |  |  |  |  |  |
| Learning Opportunity End Date |  |  |  |  |  |
| Timetable Event Resource type * | code list |  |  |  | person, location, equipment |
| Timetable Event Resource sub-type * | code list |  |  |  | depends on resource type: * tutor, assistant, lecturer etc * room, lab, playing field, virtual, etc * projector, whiteboard, etc |
| Timetable Event Learning Event Type * | code list |  |  |  |  |
| Timetable Cycle Structure |  |  |  |  |  |
| Award Claim Withheld Reason | code list |  |  |  |  |
| Award Claim Status | code list |  |  |  |  |
| Award Result Query |  |  |  |  |  |
| Award Result Appeal |  |  |  |  |  |
| Rules of Combination |  |  |  |  |  |

# Stakeholder engagement

| Role | Candidates | Organisation |
| --- | --- | --- |
| Subject matter experts | Alison Prior Alan Howe Andrew Harland Andrew Thompson Barry Eaton Claire Bushell Jana Mazuchova John Callery John Taylor Mathew Dean Neil Pratt Steve Palmer Theo Ege Tony Braithwaite David Grant Graham Mort John Perks Ann Hughes | East Surrey College Oaklands College (Herts) Examination Officers Association Joint Council for Qualifications MIAP LSC Filton College (Bristol) Hastings College (Kent) DCSF (SAU) Joint Council for Qualifications Association of Colleges Bournville College (Birmingham) DCSF (SAU) Qualifications and Curriculum Development Agency Strode College (Somerset) Norton Radstock College (Bath) Strodes College (Surrey) Association of Colleges Becta |
| Stakeholders for business review | Members of the Data Special Interest Group |  |
| Standards developers | Steve Palmer David Foster Tim Wood Terry Knowles | DCSF Strategy and Architecture Unit DCSF Strategy and Architecture Unit TSS TSS |
| Standards development peer review | Steve Palmer David Foster Tim Wood Terry Knowles | DCSF Strategy and Architecture Unit DCSF Strategy and Architecture Unit TSS TSS |
| Adoption review | Members of SIFA, other system vendors | SIFA Other vendor group, representation to be agreed |
| Internal ESCS IT departments | To be agreed | To be agreed |
| Any other stakeholder |  |  |

# Costs and resources

Service and the DCSF Strategy and Architecture Unit.

It is estimated the development will take around 12 man days

# Risks

| Issue | Mitigation |
| --- | --- |
| Significant effort is needed to put code lists in place for Registrations, including agreement on the identification of learning providers, curriculum delivery centres, assessment Centres and lines of learning. | Combining existing identifiers as far as possible to ensure uniqueness for example local authority codes, together with identification rules |
| Defining a single process, roles and terminology that meets the needs of (i.e. can be translated into terminology) needed for all education sectors may take time. | The activity must be time-boxed to deliver in September. Alignment to the needs of the whole of education may need to follow later, and may require revisions to the standards. |

# Work plan and timeline

The table below summarises key milestones for the development of business standards to meet this business case.

| Milestone | Planned Date |
| --- | --- |
| Draft Business Case Produced | 10/08/09 |
| Business Case Approved | 11/09/09 |
| Draft Data Standard Produced | Early September |
| Approved Data Standard | End November |

Enterprise Architecture for the Education, Skills and Children’s Services ‘System’  Business Data Architecture – Version 2.03